Bootcamp Journey

Use this document as a high-level overview of your journey.

This document will reference both these aspects:

- Technical Skills Development

  - Core ML/AI Concepts

  - Gen AI & Data Engineering

  - MLOps & Deployment

- Project-Based Learning

  - Agile Scrum Methodology

  - Team Collaborations

  - Real-world Applications

Project Timeline

Here is a high-level timeline of your 11-week journey.

Week 1 - 11 Agenda for AI PM Bootcamp

- Week 1: Learning and Onboarding Study all the AI knowledge:

  - Training for AI Engineers

  - Engineers’ Training Youtube Playlist

  - Training of AI Designers

  - Designers’ Training Playlist

  - Engineers: Working on Job Assistant Agent or Discord RAG FAQ Chatbot

    - Make sure to join Office hours to discuss your thoughts and issues with these projects. (every Saturday)

- Week 2: Learning and Onboarding Study all the AI knowledge:

  - Engineers/Data Scientists

    - Training for AI Engineers

    - Engineers’ Training Youtube Playlist

  - Designers

    - Training of AI Designers

    - Designers’ Training Playlist

  - Designers:  Join Pitch Day & Team Match (within 24 fill out AI products interested in on Team Match.xls for Cohort 7) -

    - Designers and PM’s need to reach out to each other and determine if they are a good match. Each team can initially have 2 designers. (1 - Senior + 1 - Junior)

      - Format: Full_Name(Role - Senior/Junior)

        - Senior 2 or more years of experience

    - After designers join the team: Discuss User Interview process [PM to lead this discussion] ⇒Prioritize Fast matching this week

    - Main communication = Discord (check daily)

  - Engineers: Working on Job Assistant Agent or Discord RAG FAQ Chatbot

    - Make sure to join Office hours to discuss your thoughts and issues with these projects.

- Week 3: Continue development

  - Designer building High-Fidelity Designs

    - User Interviews (continue)

    - Prepare for Week 4 presentation to Engineers/Data Scientists

  - Engineers: Working on Job Assistant Agent or Discord RAG FAQ Chatbot

    - Make sure to join Office hours to discuss your thoughts and issues with these projects.

    - Submit your code and video walk through of code logic and provide a running example by filling out this Google Form

- Week 4: Prepare and Join Pitch Day & Ranking

  - Designers & PM present to Engineers

  - Engineers join Zoom Pitch Day and fill out Google Ranking form. (Lead Engineers get Ranking choice priority)

    - Lead Engineer Responsibilities =

      - Lead System Architecture Design (Bring thoughts to Office Hours)

      - Determine version control process in shared repository (Github) [And Git locally]

      - Assist other Engineers (not code for them but help with issues/hurdles)

      - Help PM’s with technical hurdles

- Week 5: Cross-functional team collaboration. Agile feature development

- Week 6: Cross-functional team collaboration. Agile feature development

- Week 7 Cross-functional team collaboration. Agile feature development

- Week 8: Cross-functional team collaboration. Agile feature development

- Week 9: Cross-functional team collaboration. Agile feature development

- Week 10: Testing and Demo ready

- Week 11: Demo!

Training Documents:

- Training for Engineers (Click link)

- Training for Designers (Click link)

- Transformers Illustrated

  - The Illustrated Transformer – Jay Alammar

- Andrej Karpathy's Neural Networks Zero to Hero

  - Neural Networks: Zero to Hero - YouTube

- HuggingFace Course

  - Introduction - Hugging Face NLP Course

Gen AI & Data Engineering (4 Days)

Generative AI for Beginners | Microsoft Learn

    - Day 1-2: LLM Fundamentals

      - LLM architectures

      - Prompt engineering

      - Context length and limitations

      - RAG (Retrieval Augmented Generation)

      - Vector databases

    - Day 3: Data Engineering

      - Data preprocessing

      - Text chunking strategies

      - Embedding models

      - Vector similarity search

      - Data quality and validation

    - Day 4: Integration

      - API integration (OpenAI, Anthropic)

      - Streaming responses

      - Error handling

      - Cost optimization

    - Practical Exercises:

      - Build a simple chatbot

      - Implement RAG system

      - Create custom training dataset

    - Resources:

      - LangChain Documentation

        - Tutorials | 🦜️🔗 LangChain

      - OpenAI Cookbook

        - GitHub - openai/openai-cookbook: Examples and guides for using the OpenAI API

      - Vector Database Fundamentals

        - What is a Vector Database & How Does it Work? Use Cases + Examples | Pinecone

MLOps & Deployment (3 Days)

    - Day 1: Development Practices

      - Git workflow

      - Code review process

      - Documentation standards

      - Testing strategies

    - Day 2: Deployment

      - Docker containerization

      - CI/CD pipelines

      - Model serving

      - API development (FastAPI)

    - Day 3: Monitoring

      - Logging best practices

      - Performance monitoring

      - Cost tracking

      - Error handling

    - Resources:

      - MLOps Zoomcamp

        - GitHub - DataTalksClub/mlops-zoomcamp: Free MLOps course from DataTalks.Club

      - FastAPI Documentation

        - FastAPI

      - Docker for ML

        - Docker For Data Scientists

Project-Based Learning (Weeks 3-11)

  - Agile Scrum Methodology (Week 3)

Please set aside 1 hour for Agile (Week 1&2)

Understanding Agile Scrum.pdf

What Is Agile Methodology? | Introduction to Agile Methodology in Six Minutes | Simplilearn

What Is Agile Scrum Framework? | Scrum Framework Explained | Agile Methodology | Simplilearn

Master the Daily Scrum: Everything You Need to Know for Agile Success! 🚀 | Scrum Basics Simplified

What are the tools and techniques for documenting and tracking scope and change in agile?

    - Sprint Structure: (team consensus)

      - 1-2 week sprints

      - Standups (15 mins)

      - Sprint planning (1 hour)

      - Sprint review (20 mins)

      - Retrospective (20 mins)

    - Documentation Requirements: (team consensus)

      - Sprint backlog

      - User stories

      - Technical documentation

      - API documentation

      - Deployment guides

    - Tools: [PM’s to choose]

      - Any free Project tracking tool (JIRA, Monday etc.)

        - https://clickup.com/

        - Google Sheets

        - https://linear.app/

        - https://taiga.io/

      - Any choice of documentation tool

      - GitHub for code management

  - Team Collaborations (Weeks 4-11)

    - Team Structure:

      - Roles:

        - Full Stack Engineer

          - Front end Engineer

          - Back end Engineer

          - Fullstack Engineer

        - Data Scientist

        - UX Designer

        - Product Manager

    - Example Weekly Schedule: (team consensus)

      - Monday: Sprint planning/review

      - 2 times Weekly: Standups

      - Wednesday: Technical discussion

      - Friday: Demo/documentation

  - Real-world Applications (Ongoing)

    - Project Requirements:

      - Business value proposition

      - Scalability considerations

      - Cost optimization

      - Security compliance

      - User experience

    - Deliverables: (team consensus)

      - Working prototype

      - Technical documentation

      - API documentation

      - Deployment pipeline

      - Monitoring dashboard

      - Final presentation

Onboarding Video Link By Anil Thomas: https://youtu.be/ZBEoZYmMCMc [Cohort 5]

Success Metrics:

- Functional prototype

- Clean, documented code

- Comprehensive testing

- Clear documentation

- Effective presentation

- Team collaboration

Tools & Technologies

[05. Tools & Technologies.docx]

Mentor Kat Sao’s Schedule & Recordings (Cohort 3)

Week 1: Friday, January 31 @11am - Duration: 1hr

Session Theme: Introduction, What to expect, Timelines, Q&A https://youtu.be/_v6hyhS_U0U

Week 2: Friday, February 7 @ 11am - Duration : 30 mins Session Theme: Q&A: General - (Session Canceled, No attendees)

Week 3: Friday, February 14 @ 11am - Duration 1hr Session Theme: Prepping for Team Matching & I’m on a team, now what?  https://youtu.be/d7bCIwlXZsY

Week 4: Friday, February 21 @ 10am - Duration 30 mins Session Theme: AI Product Lifecycle https://youtu.be/sc8g3RvwBBk

Week 5: Friday, February 28 @ 11am - Duration 30 mins Session Theme: Outcome Mindset & Delivering Value  https://youtu.be/ADjjqyM1zP4

Week 6: Friday, March 7 @ 11am - Duration 30 mins Session Theme: Q&A: Retrospective, how’s it going? (no recording) No Recording

Week 7: Friday, March 14 @ 11am - Duration 1hr Session Theme: Q&A and Retrospective -  No recording

Week 10: Friday, April 4 @ 11am - Duration 1hr Final Session Theme: Demo Practice & Retrospective  - CANCELED